## Sheet1
Date | Who | Task | Description | %Completion | Deliverable | Hours
2022-08-25 | Blackcoffer | Project Research | Task, Objective and Plan of actions | 100 |  | 2
2022-08-25 | Blackcoffer | (1) Change Event Count to Pages / Session | event count to pages/sessio in the scorecard setup | 100 |  | 1
2022-08-25 | Blackcoffer | (2) Remove all but top 3 conversions. Make chart readable. | applied filter to exclude all conversions but the top 3 mentioned | 100 |  | 2
2022-08-25 | Blackcoffer | (3) Popular pages - exclude silly pages and make readable and eliminate one of the 2 visualizations showing the same thing. | Applied filter to remove unwanted pages , removed 2 visualizations that were showing the same thing | 100 |  | 3.5
2022-08-25 | Blackcoffer | (4) Site Search should display top searches. (Since it is an autocomplete I hope to figure out a way to remove all/most of the partials. | waiting for access/Screen share work | 10 | pending | 1
2022-08-26 | Blackcoffer | (6) Work on theme for charts and scorecards | changed the theme & color for charts | 100 |  | 2
2022-08-26 | Blackcoffer | (7) Remove redundant table charts. | removed useless charts & resized others charts accordingly | 100 |  | 2
2022-08-27 | Blackcoffer | (8) add Timeseries for scorecards to user activity section | added time series chart to monitor user activity | 100 |  | 3
2022-08-29 | Blackcoffer | (9) add new functional charts to dashboard | created a number of bar graphs with views as metric | 100 |  | 3
2022-08-29 | Blackcoffer | (10) create heatmaps | created heatmaps of views & total users | 100 |  | 2
2022-08-30 | Blackcoffer | (11) add visualizatios regarding total & active users | added visualizatios regarding total & active users with multiple columns | 100 |  | 4
2022-08-31 | Blackcoffer | (12) add different variety of graphs | added new treemaps & area line chart for better visualizations | 100 |  | 2
2022-08-31 | Blackcoffer | (13) change background & arrangements | added background to existing graphs , changed graph arrangements | 100 |  | 3